## Dadaab villages
County | Garissa
Sub County | Dadaab
Ward | Dadaab
Village | Dadaab
Title | ANNUAL WORK PLAN-2020-2021
Financial Year 2020-2021
Objectives | Activities | When | Where | Qty | Unit | Rate | Estimated Cost | Q1 | Q2 | Q3 | Q4 | Persons/organizations responsible
Component 1:Social and Economic Services and Infrastructure
Improved access to quality and affordable Health care services
| Support equiping of Dadaab Sub-County Hospital Maternity unit- | 2020/2021 | Dadaab | 1 | items | 3522000 | 3522000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Support equiping of Dadaab Sub-County Hospital Laboratory unit- | 2020/2021 | Dadaab | 1 | items | 4804400 | 4804400 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Support Equiping of Dadaab Sub-County Hospital theatre- | 2020/2021 | Dadaab | 1 | items | 3294300 | 3294300 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Construction of incinerator at Dadaab -Sub-County Hospital | 2020/2021 | Weldoni | 1 | No | 3500000 | 3500000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Construction of Dispensary at Weldoni | 2020/2021 | Weldoni | 1 | No | 7500000 | 7500000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Equiping of Weldoni Dispensaary. | 2020/2021 | Weldoni | 1 | items | 3000000 | 3000000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Construction of 4 No.staff quarters(self contained single unit) Staff quarters for staff on call 2 each | 2020/2021 | Weldoni /boyar | 4 | unit | 1215550 | 4862200 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Fencing of the facility compound-1000 m long.-procurement of material | 2020/2021 | Weldoni | 1 | items | 1700000 | 1700000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Construction of 4 No pit latrines-with reinforced concrete suspended slab | 2020/2021 | Weldoni | 4 | Stance | 185500 | 742000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Fencing of Bogyar dispensary | 2020/2021 | Bogyar | 1 | no | 2400000 | 2400000
| Construction of an incenerator | 2020/2021 | Bogyar | 1 | No | 944000 | 944000
| Procure modern EPI Fridge | 2020/2021 | Bogyar | 1 | No | 800000 | 800000
| Renovation of Bogyar Dispensary-general |  | Bogyar | 1 | No. | 800000 | 800000
| Train of CPMCs | 2021/2022 | Weldoni | 1 | sessions | 150000 | 150000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Sub-project admin cost -including,photocping,printing,accommodations and other facilitations for CPMCs | 2021/2022 | Weldoni | 1 | NO. | 100000 | 100000 |  |  |  |  | Village level committee, Component Sub-Committees, FP,PIST,CPMC
| Sub-Total Health | [5 empty] | 38118900

## Agragated (hidden)
Component 1: Social and Economic Infrastructure and Services
Subcomponent 1(a): Community Investment Fund
| Sector | No. of Villages | No. of Interventions / Quantity/Acreage/HHs | Estimated Cost (Kshs)
i. | Water | 0 | 0 | 0
ii. | Health | 1 | 13 | 38918900
iii. | Roads | 1 | 3 | 0
iv. | Education | 1 | 11 | 0
v. | Sanitation | 1 | 1 | 0
vi. | Agriculture | 1 | 2 | 0
vi. | Livestock and market infrastructure | 1 | 9 | 0
vi. | Sub Total |  |  | 38918900
Subcomponent 1(b): Capacity Support for Local Planning and Decentralized Service Delivery
| CPMCs capacity building sessions | 1 | 5 | 150000
| Sub Total |  |  | 150000
Component 2: Environmental and Natural Resource Management
Subcomponent 2(a): Integrated Natural Resource Management
i. | Land Reclamation for farming | 1 | 2 | 360000
ii. | Afforestation | 1 | 2 | 0
iii. | LIPW | 1 | 9 | -4348000
| Sub Total |  |  | -3988000
Subcomponent 2(a): Access to Energy
i. | Energy Saving Stoves | 0 | 0 | 0
ii. | Lighting | 1 | 3 | 0
ii. |  | 0 | 0 | 0
| Sub Total | 0 | 0 | 0
Component 3: Livelihoods Program
Subcomponent a: Support to Traditional and Non-Traditional Livelihoods
i. | Funding self-help groups | 1 | 1 | 0
ii. | Training on market oriented skills for the youth. | 1 | 1 | 0
iii. | Support individual small scale businesses. | 1 | 1 | 0
iv. | Support successful community groups that have formed cooperative/producer organisation | 1 | 1 | 0
| Sub Total | 0 | 0 | 0
Subcomponent b: Capacity Building of Community Based Organizations for Livelihoods.
i. | Provision of trainings on employability and entrepreneurship to community groups | 1 | 1 | 0
| Sub Total | 0 | 0 | 0
| Grand Total |  |  | 35080900
0

## Sheet1 (hidden)
Component 1: Social and Economic Infrastructure and Services
Subcomponent 1(a): Community Investment Fund
| Sector | No. of Villages | No. of Interventions / Quantity/Acreage/HHs | Estimated Cost (Kshs)
i. | Water | 1 | 1 | 238314350
ii. | Health | 1 | 6 | 197805300
iii. | Roads | 1 | 2 | 8330000
iv. | Education | 1 | 10 | 52953680
v. | Sanitation | 1 | 1 | 3500000
vi. | Agriculture | 1 | 2 | 2150000
i. | Livestock and market infrastructure | 1 | 8 | 29671350
ii. | Sub Total |  |  | 139008380
Subcomponent 1(b): Capacity Support for Local Planning and Decentralized Service Delivery
| CPMCs capacity building sessions | 1 | 10 | 1050000
| Sub Total |  |  | 1050000
Component 2: Environmental and Natural Resource Management
Subcomponent 2(a): Integrated Natural Resource Management
i. | Land Reclamation for farming | 1 | 1 | 4450000
ii. | Afforestation | 1 | 1 | 3250000
iii. | LIPW | 2 | 2 | 21135000
| Sub Total |  |  | 28835000
Subcomponent 2(a): Access to Energy
i. | Energy Saving Stoves | 0 | 0 | 0
ii. | Lighting | 1 | 1 | 9175000
|  | 0 | 0 | 0
| Sub Total | 0 | 0 | 9175000
Component 3: Livelihoods Program
Subcomponent a: Support to Traditional and Non-Traditional Livelihoods
i. | Funding self-help groups | 1 | 1 | 50000000
ii. | Training on market oriented skills for the youth. | 1 | 1 | 5000000
iii. | Support individual small scale businesses. | 1 | 1 | 4000000
iv. | Support successful community groups that have formed cooperative/producer organisation | 1 | 1 | 8000000
| Sub Total | 2 | 2 | 67000000
Subcomponent b: Capacity Building of Community Based Organizations for Livelihoods.
i. | Provision of trainings on employability and entrepreneurship to community groups | 1 | 1 | 400000
| Sub Total | 0 | 0 | 400000
| Grand Total |  |  | 245468380

## DD2 (hidden)
| Intervention | No. of Villages | No. / Quantity /Acreage | Estimated Cost (Kshs)
Water
| Construction of water Kiosks | 0 | 0 | 0
| Installation of elevated tank | 0 | 0 | 0
| Construction of livestock troughs | 0 | 0 | 0
| Boreholes | 0 | 0 | 0
| Water Pans | 0 | 0 | 0
| Water Tanks | 0 | 0 | 0
| Piping and Supply of Water | 0 | 0 | 0
| Installing Pumps (Solar, etc.) | 1 | 1 | #REF!
| Sub Total | 0 | 0 | #REF!
Health
1 | Construction of Dispensaries | 1 | 1 | 7500000
2 | Construction of Health Staff Quarters | 0 | 0 | 0
3 | Renovation of Dispensaries | 0 | 0 | 0
4 | Fencing | 0 | 0 | 0
5 | Equipment for Dispensaries | 0 | 0 | 0
6 | Medical Supplies | 0 | 0 | 0
7 | Purchase of Ambulances | 0 | 0 | 0
| Construction of the facility incinerator. |  |  | 930250
| Equiping of Weldoni Dispensaary. | 1 | 1 | 2450000
| Construction of 2 No.staff quarters(self contained single unit) Staff quarters for staff on call | 1 | 1 | 2431100
| Fencing of the facility compound-1000 m long. | 1 | 1 | 2855000
| Construction of 4 No pit latrines-with reinforced concrete suspended slab | 1 | 1 | 742000
| Sub Total | 0 | 0 | 16908350
Roads
1 | Gravelling and Marram | 1 | 1 | 0
2 | Opening new roads | 0 | 0 | 0
3 | Drainage | 0 | 0 | 0
|  | 0 | 0 | 0
| Sub Total | 0 | 0 | 0
Education
1 | Construction of Classrooms | 1 | 13 | 0
2 | Renovation of Classrooms | 1 | 16 | #REF!
3 | Equipping of Schools | 1 | 5 | #REF!
4 | Construction of Teachers Houses | 0 | 0 | 0
5 | Fencing Schools | 0 | 0 | 0
6 | Construction of dormitory | 1 | 2 | 0
| Renovation of dinning hall |  |  | #REF!
| Sub Total | 0 | 0 | #REF!
Sanitation
1 | Construction of Latrines | 1 | 1 | 0
2 | Construction of Toilets | 0 | 0 | 0
|  | 0 | 0 | 0
| Sub Total | 0 | 0 | 0
|  | 0 | 0 | 0
Agriculture
1 | Land Reclaimed for Farming | 1 | 1 | 360000
2 | Fencing Farmland | 0 | 0 | 0
2 | Procurement of Farm Equipment | 0 | 0 | 0
3 | Procurement of Farm Input | 0 | 0 | 0
4 | Construction of Cattle Dips | 0 | 0 | 0
5 | Construction of Markets / Yards | 0 | 0 | 0
|  | 0 | 0 | 0
| Sub Total | 0 | 0 | 360000
| Grand Total | 0 | 0 | #REF!